## Slide 1
TECHNICAL REVIEW OF L463 30MY TPO WRAPPED PANELS
Jinrong (SH) Automotive Parts Corp., Ltd
22nd June 2026

## Slide 2
PROJECT INFORMATION
PART 01
CONTENTS
1.1 Project Basic Information
1.2 Project Development Process
1.3 Project Team Members
1.4 Project Timeline

## Slide 3
1.1 Project Information
Jaguar Land Rover –
Defender
Brand
CPT JLR China IEO Warehouse
Logistic Terms
L463 30MY
Project
10,845
Average Annual Volume
Nitra Slovakia
PLANT
11/12/2028
JOB1

## Slide 4
1.2 Project Development Process
Retrieve frozen data
Process flowchart
PFMEA
Design approval of tooling&fixture
List of sub suppliers
Control plan
PPAP recognition
New equipment/tooling and facility requirements
Technical and quality agreements with sub suppliers
PPAP Preparation
Periodic review
Periodic review
Process Design and Development
Product and Process Validation
Feedback evaluation and corrective measures
Approval of tooling & checking fixture
OTS Review
Functional testing
Design and Manufacturing of assy fixture
Skill operation training
Continuous improvement
Inspection standards
Plan and Define Projects
Feasibility analysis report/project review report
Project schedule
Test outline
Project kickoff meeting
packing design
Development Task Book
Product Design and Development
Design target and quality target
Specific product and process characristics
DV test
Initial process flow chat
2D/3D data
Initial BOM
Product quality assurance plan
Tooling and fixture list

## Slide 5
1.3 Project Team Members

## Slide 6
1.4 Project Timeline
PR release in Dec. 2026. VB MRD is May 10th 2027.
Time is short for tooling development and delivery.
Some parts need air freight according to the build plan of VB vehicles.

## Slide 7
1.5 Similar Project Experience
Vehicle: Renault XDD Interior parts
Surface Layer: TPO
TPO： 1.2mm thickness
Base: PE/MD20
Process: Mold Injection/Glue lamination
Vehicle: LUCID Midsize SUV
Surface Layer: ：Tufted
Mid Layer: PHC( PU/AL/GF)
Backing Layer: 1000gsm PET/PP backing
Proess: Hot forming + Lamination
Vehicle: FORD Bronco
Surface Layer: 1000gsmTPE+100gsm Knitted Fabric
Mid Layer: PHC( PU/Paper/GF)
Backing: 120gsm Non-woven fabric
Process: PUR glue lamination

## Slide 8
PARTS LIST AND
PROCESS ANALYSIS
PART 02
CONTENTS
2.1 RFQ Information
2.2 BOM
2.3 Question List
2.4 Production Process
2.5 Sub-suppliers List
2.6 PFMEA

## Slide 9
2.1 RFQ-Product
Exploded View: 6 SEAT ACCESS PANEL (CAD REFERENCE: EI_ Z7B2-13A994-AAW )
Sr.no. | Part Name | Qty. | Remark
1 | 6 SEAT ACCESS PANEL | 1 | IM Process
2 | ITW MAT CLIP | 1 | Clip Assy Process
3 | W780230-S CLIP STANDARD | 8 | Clip Assy Process
2
3
Injection moulding (grained) + Clip Assy

## Slide 10
2.1 RFQ-BOM
Injection moulding (grained) + Clip Assy
No. | Part Number | PART DESIGNATION | Material Information | Size（mm） | Total Weight (kg) | Sub-supplier Proposal
1 | Z7B2-13A994-AAW | 6 SEAT ACCESS PANEL REAR | Assembly |  |  | /
1.1 | Z7B2-13A994-AAW | 6 SEAT ACCESS PANEL REAR | ABS (Magnum 3325) | 490*329*52 | 0.45 | Trinseo
1.2 |  | ITW CLIP | PA66+GF30/ POM |  | 1 couple (upper+lower) | ITW
1.3 |  | W780230-S CLIP STANDARD | BS 1449 CS70 / HS70 |  | 8 pieces | 
Proposed Material - ABS MAGNUM 3325
Colour – Shadow
Grain – TBC

## Slide 11
2.2 Production Process
TPO WRAPPED PANELS
Material Drying
Part Taking & Edge Trimming
Injection Molding
Assembly process
Packing & Cooling
Dimensional & Visual Inspection
Packaging
Injection molding machine
# | Tooling | Lead time | Supplier
1 | Injection Mold*1 | 75D | /
2 | Dimensional & Visual Inspection Fixture*1 | 60D | /
Tooling & Checking fixture
Equipment lists
# | Equipment | Type | Supplier
1 | Injection Molding Machine | 900T | /
Injection moulding (grained) + Clip Assy

## Slide 12
LIST OF TOOLING
AND GAUGE
PART 03
CONTENTS
3.1 Equipment List
3.2 Tooling and Gauge List
3.3 Production Capacity Analysis

## Slide 13
3. Production Equipment and Tooling list
# | Equipment | Existing QTY | Free Capactiy | Required Capacity | Comments
1 | Injection Molding Machine | 2 | 50% | 4% | 900T
# | Tooling | QTY | Lead time (days) | Cavity | Note
1 | Injection Mold + grain | 1 | 75 | 2 | With grain
2 | Clip Assembly fixture | 1 | 40 | 1 | 
3 | Dimensional & Visual Inspection Fixture | 1 | 60 | 1 | 

## Slide 14
EXPERIENCE WITH SIMILAR TOOLING AND CHECKING FIXTURES
PART 04
CONTENTS

## Slide 15
4. Similar Product Experience
Plastic injection molding - Similar Parts
  Mold Flow
Thickness
Shrink Mark
Tempreture
Pressure
Clip Assembly Fixture
Video Inspection Fixture

## Slide 16
PACKAGING & LOGISTICS
PART 05
CONTENTS

## Slide 17
5. Packaging & Logistics
CPT Shanghai Lingang JLR IEO Warehouse
Jinrong
Shanghai
Plant
JLR Nitra Slovakia
Plant
JLR IEO Warehouse
Shanghai Lingang
Logistics hub
Pacakage: Expendable Package

## Slide 18
5. Packaging & Logistics
Packaging Specifications |  |  |  |  | 
Part basic information |  |  |  |  | 
Part Number | Z7B2-13A994-A-INS-01 | Part Length(cm) | 49 | Part Width(cm) | 33
Part Height(cm) | 5.7 | Part Weight(kg) | 0.46 | Package Type | Expendable
Transport Mode | Sea freight | Part Material | ABS/PA66/Steel | Effective From | 
Photograph/Sketch |  |  |  |  | 
Part Images |  | Open Box with Parts & Dunnage |  | Primary Packaging photo | 
External Packaging Images |  | Complete Unit Load /Pallet |  | Additional Images | 
Primary Packaging - Individual Container |  |  |  |  | 
Package Material | PE bag | Tare Weight (kg) | 0.45 | Total weight(kg) | 0.46
package length(cm) | 215 | package width(cm) | 140 | Package height | 0.04mm
No. of Containers per Layer | / | No. of Layers | / | QPC | 1
Second Packaging - External container |  |  |  |  | 
Package Material | carton box | Tare Weight (kg) | 9.2 | Total weight(kg) | 10.0
package length(cm) | 1140 | package width(cm) | 940 | Package height(cm) | 410
No. of Containers per Layer |  | No. of Layers | 1 | Density: (parts/carton) | 32
Cube Packaging Information |  |  |  |  | 
Pallet Type | four way | Pallet Element | wood | Banding Type | Stretch-Film
Pallet Length(cm) | 1140 | Pallet Width(cm) | 940 | Pallet height(cm) | 130
Cartons per Layer | 1 | Layers per Pallet | 1 | Density: (parts/pallet) | 32
Additional Comments |  |  |  |  | 

## Slide 19
VALIDATION
PART 06
CONTENTS
6.1 DVP

## Slide 20
6.1 DVP
-Performance Requirements of Non-Decorated Plastics - component level tests
 |  | Material Tests (plaques) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 |  | 1 |  |  |  | 4 plaques |  |  |  | 
Duration |  | 3 days | 1 week | 2 weeks | 6 weeks | 1 day | 1 day | 1 day | 3 weeks | 1 day | 1 day | 1 day | 1 day | 1 day | 1 day | 1 day | 1 day | 2 days | 2 days | 1 day | 3 days | 3 days
Test Name |  | Resistance to Weathering |  |  |  | Micro-scratch | Scratch | Mar | Heat Age | Fluid Spotting |  | Fluid Spotting |  | Resistance of Interior Trim to Perspiration |  |  |  | Fogging - Gravimetric | Odour |  | VIAQ | Total VOC
Test Method |  | SAE J2412 |  |  |  | TPJLR.52.009 | TPJLR.52.008 | TPJLR.52.010 | TPJLR.52.352 | TPJLR.52.155 |  | TPJLR.52.155 |  | TPJLR.52.156 |  |  |  | SAE J1976 | VDA 270 |  | TPJLR.52.104 | VDA277
Description |  | 110 kJ/m² | 220 kJ/m² | 440 kJ/m² | 1430 kJ/m² | Method A | Grained only |  | 500 hrs colour assessment | Water 23 ºC | Soap 23 ºC | Water 60 ºC | Soap 60 ºC | Water | Salt | Acid | Alkali |  | 40C | 80C |  | 
Component Level Status/Report - Materials Engineering Comment |  | GS 4 min |  |  | GS 3/4 min | High gloss only No scratch | dL +0.5 max | dG 1.0 max | GS 4 min | GS 4 min |  | GS 4 min |  | GS 4 min |  |  |  | Meet requirements of STJLR.51.5229 |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | JLR |  | JLR | JLR | JLR
 |  | Component Tests |  |  |  |  |  | 
Duration |  | 10 days | 7 days | 3 days | I day | I day | 3 days | 4 days
Test Name |  | Assembly Test |  | Hygroscopic materials only - Assembly Test | Grained only |  | Parts wth Metal fixings only | 
Test Method |  | TPJLR.52.353 | TPJLR.52.352 | TPJLR.52.351 | TPJLR.52.008 | TPJLR.52.010 | See STJLR.00.5235 for details | 
Description |  | Accelerated Environmental Ageing | Resistance to Heat Ageing | Resistance to Humidity | Scratch | Mar | Corrosion - 72 hrs humidity | Cyclic Corrosion - 4 cycles for wet areas
Component Level Status/Report - Materials Engineering Comment |  | 168 hrs Assess for distortion etc |  |  | dL +0.5 max | dG = 0.6 max |  | 
 |  | Supplier | Supplier |  | Supplier | Supplier |  | 
Test evaluation completed; no issues detected.
Question: The tests not indicated RASIC are done by JLR or JINRONG

## Slide 21
THANK YOU！
Company Address
No. 58, Lane 2400, Baoan Highway, Baoshan District. Shanghal, China 201907
Presented by: Yang WANG | Tracy Wang
Mobile: +86 18516530077 | +86 15921853685
Email: wangyang@jinronggroup.cn | tracy@jinronggroup.cn