## RR TEMPLATE
FCA US LLC 【中】FCA US LLC |  |  |  | Document Number: RR-Template 【中】文件编号:RR-Template
Contact/Phone Number: TBD 【中】联系人/电话:待定
Date Published: 1/12/18
ROLES & RESPONSIBILITIES DOCUMENT 【中】角色与职责文件(RR) |  |  |  | Change Level: AA 【中】更改级别:AA
This document is to define Roles and Responsibilities for the purpose of providing quotations by suppliers for a given commodity 【中】本文件用于界定某品类供应商报价时的角色与职责
A (Acceptance) --> Acceptance to proceed but does not own the task / project. Assign "A" only when needed (not required for every task). 【中】A(认可)→ 同意推进但不拥有该任务/项目;仅在需要时指派A(并非每项任务都需要)。
R (Responsible) --> Owns the task / project and is accountable for the result. Should not proceed without Acceptance from the other party when "A" is assigned. There cannot be more than one "R" per task. 【中】R(负责)→ 拥有该任务/项目并对结果负责;若指派了A,须经对方认可方可推进;每项任务只能有一个R。
"Supplied Component" refers to the part number (s) being quoted by the individual supplier. 【中】“供货件”指各供应商所报价的零件号。
"System" referes to any vehicle system that uses the "supplied component". 【中】“系统”指使用该供货件的任何整车系统。
NA (Non-Applicable) --> If a task is non-applicable to the "Supplied Component", then leave blank and place 'NA' in the comments column. 【中】NA(不适用)→ 若某任务对供货件不适用,则留空并在备注列填'NA'。
See ACRONYM Tab for list of acronym descriptions 【中】缩写释义见 ACRONYM 页
"Supplied Component" & / or Commodity (CORE Functions) 【中】“供货件”及/或品类(核心职能)
Task and Functions 【中】任务与职能 |  | FCA US 【中】FCA US(克莱斯勒美国) | Supplier 【中】供应商 | Comments 【中】备注
1 | Identify customer requirements (VOC) 【中】识别客户需求(VOC)
2 | Participate in customer clinics / focus groups 【中】参与客户调研/焦点小组
3 | Define functional objectives (Vehicle/System/supplied component Levels) 【中】定义功能目标(整车/系统/供货件层级)
4 | Identify the relationship between the VOC & system level requirements and the functions necessary to achieve them (HoQ Phase 2) 【中】识别客户之声(VOC)与系统级要求及实现功能之间的关系(质量屋第2阶段)
5 | Identify the key functions of the system in need of Robust Optimization (Function Map) 【中】识别系统中需稳健性优化的关键功能(功能图)
6 | Identify the relationship between inputs and outputs (Ideal Function) that best represents the primary purpose of each key function selected 【中】识别最能代表各关键功能主要目的的输入输出关系(理想函数)
7 | Identify and select the test strategy (Simulation or Physical Testing) that will be used to measure the functional robustness of the selected key functions (Outer Array – Signal and Noise Strategy) 【中】确定并选择用于衡量所选关键功能稳健性的测试策略(仿真或实物测试)(外阵列-信噪策略)
8 | Demonstrate the Robustness, in terms of Signal to Noise ratio, of each of the key functions selected relative to that of other systems/Components on the market. 【中】以信噪比衡量,证明所选各关键功能相对市场上其它系统/零件的稳健性。
9 | Identify factors and levels that can be controlled that result in the least variation in performance when tested in the presence of the uncontrolled factors (Robustness as quantified in a Signal to Noise ratio) 【中】识别在存在不可控因素时使性能波动最小的可控因素及水平(以信噪比量化稳健性)
10 | Identify factors and levels that can be controlled that may result in the highest or targeted level of performance with minimal effect on Robustness. 【中】识别可控因素及水平,在对稳健性影响最小的前提下获得最高/目标性能。
11 | Identify the cost sensitivity of the factors effecting the selected functions’ robustness 【中】识别影响所选功能稳健性的各因素的成本敏感度
12 | Demonstrate that the optimized design meets all system level requirements, engineering measures and targets prior to design release. 【中】在设计发布前,证明优化设计满足所有系统级要求、工程指标与目标。
13 | Define quality targets (e.g. JD Powers, Consumer report, etc…) 【中】定义质量目标(如 J.D.Power、消费者报告等)
14 | Establish supplier timeline to support program milestones 【中】建立供应商时间表以支持项目里程碑
15 | Define tooling timelines 【中】确定模具时间计划
16 | Design "supplied component" for the FDV 【中】为骡车(FDV)设计供货件
17 | Determine tooling facility &/or part source 【中】确定模具厂及/或零件来源
18 | Identify part commonization opportunities 【中】识别零件通用化机会
19 | Define vehicle build specifications 【中】定义整车制造规范
20 | Develop system DFMEA 【中】编制系统 DFMEA
21 | Develop "supplied component" DFMEA 【中】编制供货件 DFMEA
22 | Develop "supplied component" PFMEA 【中】编制供货件 PFMEA
23 | Develop PFMEA, control plans, and assembly process for "supplied component" 【中】为供货件编制 PFMEA、控制计划及装配工艺
24 | Develop a quality plan to meet quality objectives 【中】编制质量计划以达成质量目标
25 | Develop quality improvement proposals for review with FCA US Engineering 【中】编制质量改进提案,与 FCA US 工程评审
26 | Provide sub-suppliers quality plan and documentation 【中】提供二级供应商质量计划及文档
27 | Select all "supplied component" materials 【中】选定所有供货件材料
28 | Ensure material compatibility with interfacing parts & environment 【中】确保材料与配合件及环境的相容性
29 | Ensure no negative influences that could potentially act on the "supplied component" (e.g. temperature, humidity, UV, fluids, etc…) 【中】确保对供货件无潜在不利影响(如温度、湿度、UV、油液等)
30 | Ensure product integrity within the package constraints of the system/Vehicle 【中】在系统/整车的布置约束内确保产品完整性
31 | Error proof "supplied component" 【中】对供货件做防错
32 | Provide detail "supplied component" drawings, including structured serviceable sub-components 【中】提供供货件详细图纸,含结构化可维修子件
33 | Resolve all "supplied component" DMA interferences 【中】解决所有供货件数字样机干涉
34 | Resolve all system DMA interferences 【中】解决所有系统数字样机(DMA)干涉
35 | Resolve Vehicle integration DMA interferences 【中】解决整车集成数字样机干涉
36 | Perform CAE Analysis (Finite Element Analysis,...) for "supplied component" 【中】对供货件做 CAE 分析(有限元分析等)
37 | Design production intent check fixtures &/or gauges 【中】设计量产意图检具/量规
38 | Design "supplied component" tool (prototype &/or production) 【中】设计供货件模具(样件模及/或量产模)
39 | Coordinate program tracking meetings 【中】组织项目跟踪会议
40 | Support program tracking meetings 【中】支持项目跟踪会议
41 | Support all packaging and feasibility studies (on site if necessary) 【中】支持所有包装与可行性研究(必要时到现场)
42 | Provide "supplied component" simulation/prototypes 【中】提供供货件仿真/样件
NOTE: Add any other tasks and functions that will impact supplier quotation for the given commodity 【中】注:补充会影响该品类供应商报价的其它任务与职能
"Supplied Component" & / or Commodity (CORE Functions) 【中】“供货件”及/或品类(核心职能)
Task and Functions 【中】任务与职能 |  | FCA US 【中】FCA US(克莱斯勒美国) | Supplier 【中】供应商 | Comments 【中】备注
43 | Perform "supplied component" dimensional and functional test 【中】对供货件做尺寸与功能测试
44 | Responsible for DV testing cost 【中】负责 DV 测试费用
45 | Procure any required interfacing parts for DV testing 【中】采购 DV 测试所需的配合件
46 | Conduct "supplied component" lab DV test 【中】进行供货件实验室 DV 测试
47 | Perform DV testing of Pre-VP parts (includes impact parts) 【中】对 Pre-VP 件做 DV 测试(含碰撞件)
48 | Conduct vehicle "supplied component" DV test 【中】进行整车供货件 DV 测试
49 | Establish "supplied component" DVP&R documentation 【中】建立供货件 DVP&R 文档
50 | Maintain "supplied component" DVP&R documentation 【中】维护供货件 DVP&R 文档
51 | Establish system DVP&R documentation 【中】建立系统 DVP&R 文档
52 | Maintain system DVP&R documentation 【中】维护系统 DVP&R 文档
53 | Establish and maintain vehicle level DVP&R documentation 【中】建立并维护整车级 DVP&R 文档
54 | Conduct vehicle system testing 【中】进行整车系统测试
55 | Provide Pre-VP part dimensional certification 【中】提供 Pre-VP 件尺寸认证
56 | Review and report on assembly plant defects 【中】评审并报告装配厂缺陷
57 | Provide cost, weight & investements (CWI) revision for program direction changes (CN). 【中】针对项目方向变更(CN)提供成本、重量、投资(CWI)修订。
58 | Perform a weight optimization study to ensure that the supplier's product is the lightest possible design that meets or exceeds all functional and performance objectives. 【中】做轻量化研究,确保产品在满足/超越所有功能与性能目标前提下重量最轻。
59 | Identify and select the weight optimization strategy (CAE Topology Optimization software or Physical testing). For structural (load bearing) components or systems, a CAE topology optimization study is required. 【中】确定并选择轻量化策略(CAE 拓扑优化软件或实物测试);承载结构件/系统须做 CAE 拓扑优化研究。
60 | In case where advanced light weight materials are used, a weight optimization study is still required to identify even further weight savings. 【中】即使采用先进轻量化材料,仍需做轻量化研究以挖掘进一步减重空间。
61 | Submit documentation showing that the weight optimization study has been completed, clearly identifying weight savings amount and graphically showing weight savings locations as compared to one or more relevant best-in-class reference designs. 【中】提交轻量化研究完成证明,明确减重量并以图示标出减重位置,与一个或多个同类最佳基准设计对比。
62 | Compliant with Substance of Concern requirements (SoC) as per CS-11991 【中】符合 CS-11991 关注物质(SoC)要求
63 | Submit all structured bills of material for assemblies to Service Parts Analysis 【中】向服务件分析提交所有总成的结构化 BOM
64 | Define serviceability of assembly and subcomponents 【中】定义总成及子件的可维修性
65 | Provide detail drawings of all serviceable components as defined by Service Parts Analysis 【中】按服务件分析要求,提供所有可维修件的详细图纸
66 | Complete the Supplier Design Acceptance Process/Checklist which includes the applicable portions at Step 2, Step 3, and Step 5. 【中】完成供应商设计接受流程/检查表(含第2、3、5步的适用部分)。

## ADP
FCA US LLC 【中】FCA US LLC |  |  |  | Document Number: RR-Template 【中】文件编号:RR-Template
Date Published: 1/12/18
AUTHORITY DEFINITION PLAN (ADP) DOCUMENT 【中】权责界定计划(ADP)文件 |  |  |  | Change Level: AA 【中】更改级别:AA
This document is to assist in the determination of financial responsibility for warranty expense for a given commodity 【中】本文件用于协助界定某品类保修费用的财务责任
A (Acceptance) --> Acceptance to proceed but does not own the task / project. Assign "A" only when needed (not required for every task). 【中】A(认可)→ 同意推进但不拥有该任务/项目;仅在需要时指派A(并非每项任务都需要)。
R (Responsible) --> Owns the task / project and is accountable for the result. Should not proceed without Acceptance from the other party when "A" is assigned. There cannot be more than one "R" per task. 【中】R(负责)→ 拥有该任务/项目并对结果负责;若指派了A,须经对方认可方可推进;每项任务只能有一个R。
"Supplied Component" refers to the part number (s) being quoted by the individual supplier. 【中】“供货件”指各供应商所报价的零件号。
"System" referes to any vehicle system that uses the supplied "supplied component". 【中】“系统”指使用该供货件的任何整车系统。
These fields on this page are all auto generated from the RR Template 【中】本页字段均由 RR 模板自动生成
"Supplied Component" & / or Commodity (CORE Functions) 【中】“供货件”及/或品类(核心职能)
Task and Functions 【中】任务与职能 |  | FCA US 【中】FCA US(克莱斯勒美国) | Supplier 【中】供应商 | Comments 【中】备注
1 | Identify customer requirements (VOC) 【中】识别客户需求(VOC) | R 【中】R=负责(Responsible)
3 | Define functional objectives (Vehicle/System/"supplied component" Levels) 【中】定义功能目标(整车/系统/供货件层级) | R 【中】R=负责(Responsible)
21 | Develop "supplied component" DFMEA 【中】编制供货件 DFMEA | A 【中】A=认可(Acceptance) | R 【中】R=负责(Responsible)
22 | Develop "supplied component" PFMEA 【中】编制供货件 PFMEA | A 【中】A=认可(Acceptance) | R 【中】R=负责(Responsible)
27 | Select all "supplied component" materials 【中】选定所有供货件材料 | R 【中】R=负责(Responsible)
28 | Ensure material compatibility with interfacing parts & environment 【中】确保材料与配合件及环境的相容性 | A 【中】A=认可(Acceptance) | R 【中】R=负责(Responsible)
29 | Ensure no negative influences that could potentially act on the "supplied component" (e.g. temperature, humidity, UV, fluids, etc.) 【中】确保对供货件无潜在不利影响(如温度、湿度、UV、油液等) | A 【中】A=认可(Acceptance) | R 【中】R=负责(Responsible)
30 | Ensure product integrity within the package constraints of the system/Vehicle 【中】在系统/整车的布置约束内确保产品完整性 | R 【中】R=负责(Responsible)
| Sum design responsibility 【中】设计责任合计 | 4 | 4
| Percent responsible if warranty is design related 【中】保修为设计相关时的责任比例 | 0.5 | 0.5
| Percent responsible if warranty is Supplier process related 【中】保修为供应商过程相关时的责任比例 | 0 | 1
| Percent responsible if warranty is FCA US process related 【中】保修为 FCA US 过程相关时的责任比例 | 1 | 0

## ACRONYMS
Roles & Responsibilies Document Acronym Descriptions 【中】角色与职责文件 缩写说明
| Acronym 【中】缩写 | Description 【中】描述
| APQP 【中】先期产品质量策划(APQP) | Advanced Product Quality Planning 【中】先期产品质量策划(APQP)
| CAE 【中】CAE(计算机辅助工程) | Computer Aided Engineering 【中】计算机辅助工程(CAE)
| CN 【中】变更通知(CN) | Change Notice 【中】变更通知(CN)
| DFMEA 【中】设计FMEA | Design Failure Mode and Effect Analysis 【中】设计失效模式与影响分析(DFMEA)
| DMA 【中】数字样机装配(DMA) | Digital Model Assembly 【中】数字样机装配(DMA)
| DV 【中】设计验证(DV) | Design Verification 【中】设计验证(DV)
| DVP & R | Design Verification Plan & Report 【中】设计验证计划与报告(DVP&R)
| FDV 【中】功能开发车(骡车) | Functional Development Vehicle (mule vehicle) 【中】功能开发车(骡车)
| PFMEA 【中】过程FMEA | Process Failure Mode and Effect Analysis 【中】过程失效模式与影响分析(PFMEA)
| VOC 【中】客户之声(VOC) | Voice of the Customer 【中】客户之声(VOC)
| HoQ 【中】质量屋(HoQ) | House of Quality 【中】质量屋(HoQ)

## INSTRUCTIONS
Roles & Responsibilities (RR) Document Instructions 【中】角色与职责(RR)文件说明
RR Document Purpose 【中】RR 文件目的
This document is to define the Roles and Responsibilities for the purpose of 【中】本文件用于界定角色与职责,目的是
providing quotations by Suppliers for a given commodity. 【中】供应商对某品类进行报价。
This document is not intended to act as an engineering checklist for every task to be 【中】本文件并非用作每项任务的工程检查表,
accomplished for a given program. 【中】(以完成某个项目)。
Each sourced commodity requires a Roles & Responsibilities, RR and ADP document to be stored in ADRESS. 【中】每个定点品类都需在 ADRESS 系统中存有 RR 与 ADP 文件。
Multiple commodities can point to the same RR/ADP document. 【中】多个品类可指向同一份 RR/ADP 文件。
Only one 'R' (Responsible) per task. There can only be one owner of a task. 【中】每项任务只能有一个'R'(负责);任务只能有一个责任人。
A' (Acceptance) is only required when either the Supplier or FCA US need to review the outcome of the task. 【中】仅当供应商或 FCA US 需要评审任务结果时才需要'A'(认可)。
If a task is non applicable to your component, then leave blank and add 'NA' in the comments column. 【中】若任务对你的零件不适用,留空并在备注列填'NA'。
ADP tasks must have 'R' responsibility defined. Do not put 'NA' for these tasks. 【中】ADP 任务必须定义'R'责任,不得填'NA'。
Use the second page of RR template to add any additional cost driven tasks for a particular commodity. 【中】用 RR 模板第二页为特定品类补充其它成本相关任务。
The ADP document does not require any manual input from the engineer. It is autogenerated based on inputs 【中】ADP 文件无需工程师手动输入,基于输入自动生成
within the RR document. 【中】(在 RR 文件中)。
Once complete, the document requires approval by the commodity Supervisor and Sr. Manager through ADRESS. 【中】完成后,文件须经品类主管与高级经理通过 ADRESS 审批。