## Sheet 1
DESIGN VERIFICATION PLAN AND REPORT 【中】设计验证计划与报告(DVP&R)
System: Interior 【中】系统:内饰 |  |  | Source(s) / Supplier(s): 【中】来源/供应商: |  |  |  |  | Dept.: 【中】部门: |  |  |  | Supplier Contact: 【中】供应商联系人: |  |  |  | DVP&R No.: 【中】DVP&R 编号:
Component:2025 EJ Door Elastic Storage 【中】零件:2025 EJ 车门弹性储物 |  |  | VSC: |  |  |  |  | Releasing Engr.: 【中】发布工程师: | [7 empty] | Orig. Date: 【中】初始日期:
MY / Program: 【中】年款/项目: |  |  | P/N: 【中】件号: |  |  |  |  | Suprv. / Mgr.: James Zondag | [7 empty] | Revision: 【中】版本:
Test Plan 【中】测试计划 | [10 empty] | Test Report 【中】测试报告 |  |  |  |  | Notes 【中】备注
Item No. 【中】序号 | Performance Objective 【中】性能目标 | Test Name & Procedure 【中】测试名称与方法 | Acceptance Criteria/ Test Target 【中】合格判据/测试目标 | Test Responsibility 【中】测试责任方 | Test Type 【中】测试类型 | Test Phase 【中】测试阶段 | Sample 【中】样件 |  | Planned Timing 【中】计划时间 |  | Actual Timing 【中】实际时间 |  | % Compl | Test Results 【中】测试结果 | Pass/Fail/Suspend
[7 empty] | Qty 【中】数量 | Type 【中】类型 | Start 【中】开始 | Compl 【中】完成 | Start 【中】开始 | Compl 【中】完成
Material Level spec: 【中】材料级规范:
1 | To evaluate material specific Qualification 【中】评估材料专项认证 | Material Qualification: Buckle - MS.50042 Color - MS-JP-1-3 Cord - MS-JZ-12-20 | Must meet standard requirement 【中】须满足标准要求 | Supplier 【中】供应商 | Comp 【中】零件级(Comp) | PV 【中】工艺验证(PV) | All samples 【中】全部样件 | [5 empty] | 100%
Buckle 【中】带扣 Buckle
1.1.9 | Heat Age (test specimen required) 【中】热老化(需测试样件) | 7 days @ 85°C LP-463LB-13-01, | No discoloration, color tone or change in hue in excess of 4.5 of the AATCC Gray Scale. Maximum 3.0 Delta E. Report Delta H, Delta C and L, a, b data. 【中】AATCC 灰卡变色/色调/色相变化不超过4.5级,ΔE≤3.0;报告 ΔH、ΔC 及 L、a、b 数据。 | Supplier 【中】供应商 | Comp 【中】零件级(Comp) | PV 【中】工艺验证(PV) | 5 | [5 empty] | 100%
1.1.10 | Hardness 【中】硬度 | ASTM D2240 A Scale As received and after heat aging per line 1.1.7 | Report Must meet hardness requirements. Max 10% change after heat age | Supplier 【中】供应商 | Comp 【中】零件级(Comp) | PV 【中】工艺验证(PV) | 5 | [5 empty] | 100%
1.1.11 | Xenon Resistance (test specimen required) 【中】氙灯老化(需测试样件) | SAE J2412 112.8 kJ/m² | No fade or color change in excess of the #4 rating on the ISO Gray scale for evaluating change in color. No noticeable tackiness, separation, or other detrimental change. 【中】ISO 灰卡变色不超过4级;无明显发粘、分离或其它有害变化。 | Supplier 【中】供应商 | Comp 【中】零件级(Comp) | PV 【中】工艺验证(PV) | 5 | [5 empty] | 100%
1.1.12 | Resistance to Humidity/Hot/Cold Cycling (test specimen required) 【中】耐湿热/冷热循环(需测试样件) | LP-463LB-12-01 Method B 16 hrs at 95-100%RH & 40°C, 8 hrs at -30°C, 24 hrs at 85°C per cycle 2 cycles | No fade or color change in excess of #4-5 rating on the ISO gray Scale for evaluation change in color and no other detrimental change. Report dimensional changes (in %) in both directions. | Supplier 【中】供应商 | Comp 【中】零件级(Comp) | PV 【中】工艺验证(PV) | 5 | [5 empty] | 100%
1.1.13 | Resistance to Condensing Humidity (test specimen required) 【中】耐凝露湿热(需测试样件) | ASTM D1735-92 100 hrs at 95-100% RH @ 38°C | No fade or color change in excess or #4-5 on the ISO gray scale for evaluation change in color and other detrimental change. Report dimensional changes (in %) in both directions. | Supplier 【中】供应商 | Comp 【中】零件级(Comp) | PV 【中】工艺验证(PV) | 5 | [5 empty] | 100%
1.1.15 | Resistance to efflorescence/exudation (test specimen required) 【中】耐析白/渗出(需测试样件) | FIAT 9.03107 para. 2.5.17 Methods A/B | No florescense, blooming, exudation, tackiness, and/or changes in color. 【中】无析出、泛白、渗出、发粘和/或变色。 | Supplier 【中】供应商 | Comp 【中】零件级(Comp) | PV 【中】工艺验证(PV) | 5 | [5 empty] | 100%
1.1.16 | Odor 【中】气味 | SAE J1351 | No disagreeable odor either wet or dry at any temperature up to 85°C. 【中】在不超过85°C的任何温度下,干或湿状态均无异味。 | Supplier 【中】供应商 | Comp 【中】零件级(Comp) | PV 【中】工艺验证(PV) | 5 | [5 empty] | 100%
1.1.17 | Fogging, photometric (fog plate requried) 【中】雾化(光度法,需雾化板) | LP-463DB - 12 - 01 3 samples | 70 min. Formation of crystals and/or droplets is reason for rejection. | Supplier 【中】供应商 | Comp 【中】零件级(Comp) | PV 【中】工艺验证(PV) | 5 | [5 empty] | 100%
1.1.18 | Flammability <S> | FMVSS 302 (If the maximum burn rate exceeds 90 mm/min or the average exceeds 85 mm/min, an additional 10 specimens in both directions must be burned.) | 101.6 mm/min MAX | Supplier 【中】供应商 | Comp 【中】零件级(Comp) | PV 【中】工艺验证(PV) | 5 | [5 empty] | 100% |  |  | Completed Compliance Report Form must be included with test results. 【中】测试结果须附完整的合规报告表。
1.1.19 | Cold Flexability (Cold Cracking) (test specimen required) 【中】低温柔韧性(低温开裂)(需测试样件) | LP-463LB-11-01 Method B As received and after heat aging per line 1.1.7 2.54 cm (1.0in) diameter mandrel, -30°C | No cracking, breaking, or shattering. 【中】无开裂、断裂或碎裂。 | Supplier 【中】供应商 | Comp 【中】零件级(Comp) | PV 【中】工艺验证(PV) | 5 | [5 empty] | 100%
1.1.20 | Taber Wear Resistance (test specimen required) 【中】Taber 耐磨(需测试样件) | ASTM D3884 H18 abrasive wheels 2000 cycles 1000 g load | No wear through of material. (NOTE: Additional samples tested to 400 cycles may be required for review with the construction package submission. Requirements for these samples: No noticeable or max. of slight noticeable wear). | Supplier 【中】供应商 | Comp 【中】零件级(Comp) | PV 【中】工艺验证(PV) | 5 | [5 empty] | 100%
1.1.21 | Dimensional Stability 【中】尺寸稳定性 | ASTM D1204 after 6 hours heat age per line 1.1.7 | Report dimensional changes (in %) in both directions. 【中】报告两个方向的尺寸变化(%)。 | Supplier 【中】供应商 | Comp 【中】零件级(Comp) | PV 【中】工艺验证(PV) | 5 | [5 empty] | 100%
1.1.22 | Salt Solution Immersion (3%) (test specimen required) 【中】盐水浸泡(3%)(需测试样件) | MS-DC-643, Table 2.12 The part shall be exposed to 8 hours immersion followed by 16 hours min drying in room temperature per cycle. Cycle whole part 10 times. Rinse samples to remove salt deposits. | No changes in appearance or other detrimental changes. 【中】外观无变化,也无其它有害变化。 | Supplier 【中】供应商 | Comp 【中】零件级(Comp) | PV 【中】工艺验证(PV) | 5 | [5 empty] | 100%
1.1.23 | Scratch and Mar Resistance (test specimen required) 【中】耐划伤与耐擦伤(需测试样件) | LP-463DD-18-01 Five Finger Scratch Test Use 1mm diameter scratch pin. 4, 6, 8, 10 and 15N loads. | Surface shall not show significant discoloration or gloss change at or below the 10 N load level. The test sample shall achieve a minimum of 4 on the AATCC Gray Scale. Surface of part may not stress whiten when exposed to 10N scratch pin Results must be submitted and approved by engineer and materials engineer | Supplier 【中】供应商 | Comp 【中】零件级(Comp) | PV 【中】工艺验证(PV) | 5 | [5 empty] | 100%
CORD-ELASTOMER 【中】绳-弹性体
| Thickness 【中】厚度 | ASTM D3774 | As specified for application 【中】按应用规定 | Supplier 【中】供应商 | Comp 【中】零件级(Comp) | PV 【中】工艺验证(PV) | 5 | [5 empty] | 100%
| Tensile Strength, N 【中】拉伸强度(N) | ASTM D5034 | 400 N | Supplier 【中】供应商 | Comp 【中】零件级(Comp) | PV 【中】工艺验证(PV) | 5 | [5 empty] | 100%
| Elongation @ 44 N | ASTM D5034 | 40 +/- 12% | Supplier 【中】供应商 | Comp 【中】零件级(Comp) | PV 【中】工艺验证(PV) | 5 | [5 empty] | 100%
| Resistance to Heat Aging (7 days at 85°C ) 【中】耐热老化(85°C 7天) | LP-463LB-13-01 | There shall be no noticable degradation, separating, or other detrimental change to material 【中】材料不得有明显劣化、分离或其它有害变化 | Supplier 【中】供应商 | Comp 【中】零件级(Comp) | PV 【中】工艺验证(PV) | 5 | [5 empty] | 100%
| Resistance to Crocking 【中】耐摩擦色牢度 | SAE J861 | Minimum of 4 AATCC scale, also report Delta E, Delta H, Delta C, and L, a, b. 【中】AATCC 灰卡≥4级,并报告 ΔE、ΔH、ΔC 及 L、a、b。 | Supplier 【中】供应商 | Comp 【中】零件级(Comp) | PV 【中】工艺验证(PV) | 5 | [5 empty] | 100%
| Colorfastness to water 【中】耐水色牢度 | AATCC TM107 | Minimum of 4 AATCC scale. 【中】AATCC 灰卡≥4级。 | Supplier 【中】供应商 | Comp 【中】零件级(Comp) | PV 【中】工艺验证(PV) | 5 | [5 empty] | 100%
| Resistance to Fade Xenon-225.6 kJ/m2 【中】氙灯耐褪色 225.6 kJ/m² | SAE J1885 | Minimum of 4 AATCC scale, also report Delta E, Delta H, Delta C, and L, a, b. 【中】AATCC 灰卡≥4级,并报告 ΔE、ΔH、ΔC 及 L、a、b。 | Supplier 【中】供应商 | Comp 【中】零件级(Comp) | PV 【中】工艺验证(PV) | 5 | [5 empty] | 100%
| Burn Rate 【中】燃烧速率 | SAE J369/ ISO 3795 | Maximum of 100mm/min. 【中】最大 100mm/分钟。 | Supplier 【中】供应商 | Comp 【中】零件级(Comp) | PV 【中】工艺验证(PV) | 5 | [5 empty] | 100%
100%
Fasteners 【中】紧固件
| Coating on mechanical fasteners 【中】机械紧固件镀层 | 52605_07 whichever is applicable | Must comply 【中】须符合 | Supplier 【中】供应商 | Comp 【中】零件级(Comp) | DV 【中】设计验证(DV) | 5 | [5 empty] | 100% |  |  | Fasteners Grade & surface treatment / coating details & reports not provided. 【中】未提供紧固件等级、表面处理/镀层细节及报告。
| PS-12182 | COATING SYSTEM - BLACK, GALVANIC PROTECTION BASED 【中】涂层体系-黑色,电镀防护型 | All fasteners / loose hardware shall be coated in full compliance with PS-12182 【中】所有紧固件/松散五金件须完全按 PS-12182 镀涂 | Supplier 【中】供应商 | Comp 【中】零件级(Comp) | PV 【中】工艺验证(PV) | 5 | [5 empty] | 100% |  |  | Not Done 【中】未完成
| PS.20006 | TORQUE TIGHTNESS - METRIC THREADED PARTS 【中】拧紧扭矩-公制螺纹件 | Must meet the standard 【中】须满足标准 | / | Comp 【中】零件级(Comp) | DV 【中】设计验证(DV) | 5 | [5 empty] | 100% |  |  | Over tightning test carried out at supplier end. 【中】过拧测试在供应商端进行。
100%
Additional Material Color Durability Tests: 【中】附加材料颜色耐久测试:
2 | To evaluate color durability of interior material 【中】评估内饰材料颜色耐久 | Material Qualification - MS-JP-1-3 【中】材料认证-MS-JP-1-3 | Must meet standard requirement 【中】须满足标准要求 | Supplier 【中】供应商 | Comp 【中】零件级(Comp) | PV 【中】工艺验证(PV) | 5 | [5 empty] | 100%
2.1 | Soiling Resistance (test specimen required) 【中】耐沾污性(需测试样件) | LP-463KC-04-02 Procedure 1-soil (100 cycles), Procedure 2-clean | Procedure 1 - Report results Procedure 2 - Minimum of 4 on AATCC Gray Scale for evaluating resistance to staining. | Supplier 【中】供应商 | Comp 【中】零件级(Comp) | PV 【中】工艺验证(PV) | 5 | [5 empty] | 100%
2.2 | Cleanability (test specimen required) 【中】易清洁性(需测试样件) | LP-463KC-04-01 Grease & General Cleanability | No noticeable ringing, color change, or other detrimental effects. Minimum of 4 on AATCC Gray Scale for evaluating resistance to staining. | Supplier 【中】供应商 | Comp 【中】零件级(Comp) | PV 【中】工艺验证(PV) | 5 | [5 empty] | 100%
2.3 | Crocking (test specimen required) 【中】摩擦色牢度(需测试样件) | SAE J861 Wet and Dry | Minimum of 4 on AATCC Gray scale and a maximum of 3.0 Delta E. Report Delta H, Delta C, and L, a, b data. 【中】AATCC 灰卡≥4级、ΔE≤3.0;并报告 ΔH、ΔC 及 L、a、b 数据。 | Supplier 【中】供应商 | Comp 【中】零件级(Comp) | PV 【中】工艺验证(PV) | 5 | [5 empty] | 100%
Component Level Tests: 【中】零件级测试:
| Strap Attachment Strength Test – 【中】绑带连接强度测试 – | Load Normal to the Door Panel Surface PF.90058 Section 7.38.1 【中】垂直于门板表面加载,PF.90058 第7.38.1节 | Stay Retained 【中】保持固定不脱落 | Supplier 【中】供应商 | Comp 【中】零件级(Comp) | PV 【中】工艺验证(PV) | 5 | [5 empty] | 100%
| Strap Attachment Strength Test – 【中】绑带连接强度测试 – | Load Vertical to the Door Panel Surface PF.90058 Section 7.38.2 【中】门板表面法向加载,PF.90058 第7.38.2节 | Stay Retained 【中】保持固定不脱落 | Supplier 【中】供应商 | Comp 【中】零件级(Comp) | PV 【中】工艺验证(PV) | 5 | [5 empty] | 100%
| Strap Long Term Set Test 【中】绑带长期永久变形测试 | PF.90058 Section 7.38.3 | Maintain Appearance 【中】保持外观 | Supplier 【中】供应商 | Comp 【中】零件级(Comp) | PV 【中】工艺验证(PV) | 5 | [5 empty] | 100%
8 | Homologation requirements 【中】法规认证要求 | PF-Homologation | Must comply 【中】须符合 | / | Comp 【中】零件级(Comp) | DV 【中】设计验证(DV) | 1 | [5 empty] | 100%
| Appearance Requirements 【中】外观要求 | AS-10119 | Must meet the general guidelines of the standard 【中】须满足该标准的总体要求 | Supplier 【中】供应商 | Comp 【中】零件级(Comp) | PV 【中】工艺验证(PV) | 1 | [5 empty] | 100%
9 | Marking 【中】标识/打标 | Must conform to CS-11000 & PS-4480 【中】须符合 CS-11000 与 PS-4480 | Shall comply 【中】须符合 | Supplier 【中】供应商 | Comp 【中】零件级(Comp) | PV 【中】工艺验证(PV) | 1 | [5 empty] | 100%
10 | Regulatory 【中】法规 | IMDS Data entered into Database 【中】IMDS 数据已录入数据库 | IMDS Data available in IMDS before part is released 【中】零件发布前 IMDS 数据须在 IMDS 系统中可查 | Supplier 【中】供应商 | Comp 【中】零件级(Comp) | PV 【中】工艺验证(PV) | 1 | [5 empty] | 100% |  |  | Enter here the acceptance transaction number for/by each part number. 【中】在此填写每个零件号的验收交易号。
11 | Regulatory 【中】法规 | CS-9003 Recycling Requirements 【中】CS-9003 回收要求 | All materials, procedures, processes, components, or systems must conform to the current regulatory (governmental) requirements regarding regulated substances and recycle ability. 【中】所有材料、程序、工艺、零件或系统须符合现行受管控物质与可回收性的法规(政府)要求。 | Supplier 【中】供应商 | Comp 【中】零件级(Comp) | DV 【中】设计验证(DV) | 1 | [5 empty] | 100%
System Level Tests: 【中】系统级测试:
12 | To check that part meet its build objectives 【中】检查零件是否达成制造目标 | Fit and Finish 【中】配合与外观 | The product should meet build objective measurement by Jury Evaluation. There should be ample clearance from the accelerator pedal (minimum 40mm) and brake/clutch pedals (minimum 10mm) at all pedal positions. 【中】产品须通过评审团评估达成制造目标;在所有踏板位置,与油门踏板(≥40mm)、刹车/离合踏板(≥10mm)须有充足间隙。 | / | System 【中】系统 | PV 【中】工艺验证(PV) | 1 | [5 empty] | 100%
13 | Performance of part in thermal loading 【中】零件热负荷下的性能 | As per Section B-2-a of PF-8673 | Part shall not yield, crack, show any kind of stress or experience any kind loss of retention from thermal loading 【中】零件在热负荷下不得屈服、开裂、出现应力或任何固定失效 | Supplier 【中】供应商 | System 【中】系统 | DV PV 【中】DV/PV | 3 3 | DV PV 【中】DV/PV |  |  |  |  | 100%
Mechanical Requirements 【中】机械性能要求
14 | Structural loading of bag handle 【中】袋提手结构承载 | Bag/handle must withstand content loads of 10lbs 【中】袋/提手须承受10磅内容物负载 | No fractures and must withstand the load without any yield 【中】无断裂,且承载下不得屈服 | Supplier 【中】供应商 | System 【中】系统 | ED/FEA DV PV 【中】ED/FEA、DV、PV | 1 4 4 | ED/FEA DV PV 【中】ED/FEA、DV、PV |  |  |  |  | 100%
Duty Cycle Tests: 【中】工作循环测试:
| Door Trim Slam Test Requirements 【中】门饰摔门测试要求 | PF.90058 Section 9.3.1 | Satisfy Door Slam Durability 【中】满足摔门耐久 | [9 empty] | 100%
| Door Trim Vibration Test Requirements 【中】门饰振动测试要求 | PF.90058 Section 9.3.2 | Satisfy Door Vibration Durability 【中】满足车门振动耐久 | [9 empty] | 100%
| Flexible Strap Storage Cycle Test 【中】柔性绑带存放循环测试 | PF.90058 Section 9.5.1 (Items stored) | Part Maintains Appearance / Function 【中】零件保持外观/功能 | [9 empty] | 100%
| Flexible Strap Storage Cycle Test 【中】柔性绑带存放循环测试 | PF.90058 Section 9.5.2 (Pull Device Door Closure) | Part Maintains Appearance / Function 【中】零件保持外观/功能 | [9 empty] | 100%
100%
Vehicle Level Tests: 【中】整车级测试:
15 | To test the durability of the Cargo net 【中】测试货网耐久性 | SXV durability run at CPG 【中】在 CPG 做 SXV 耐久试验 | To record if there are any issues 【中】记录是否存在问题 | / | Vehicle 【中】车型 | DV PV 【中】DV/PV | 2 2 | DV PV 【中】DV/PV |  |  |  |  | 100%
16 | BSR Evaluation 【中】异响(BSR)评估 | As per DS-107 | No BSR issues 【中】无异响(BSR)问题 | / | Vehicle 【中】车型 | DV PV 【中】DV/PV | 1 1 | DV PV 【中】DV/PV |  |  |  |  | 100%
Performance Objective The quantifiable/measurable statement that is to be verified through testing, evaluation, etc. |  | Test Name & Procedure Specific test title and applicable reference procedure or standard. If needed provide a brief/concise description. | Acceptance Criteria The quantifiable time or performance value that each test sample must achieve (i.e. < 22cc/m @ 5psi). Test Target Specific statement regarding test requirements (i.e. R90/C90, R90C70, P90/C90, P99/C90, No Failures per requirements, etc.). | [5 empty] | Sample Type: CAE - Virtual Analysis PHM = Prototype-hand made. PT = Prototype-tooled. Pre-VP = Pre-Verification of Process. VP = Verification of Process. PVP = Pre Volume Production. Job 1 Offline. |  | Sample Type: Alpha (P/T) Beta (P/T) Gamma (P/T) Pre-Pilot (P/T) Pilot (P/T) |  |  | Test Results State quantifiable test results based on specified Acceptance Criteria & Test Target.
| Test Phase: 【中】测试阶段: | Test Type: 【中】测试类型: | Sample Type: 【中】样件类型:
| ED 【中】工程设计(ED) | Virtual 【中】虚拟 | CAE 【中】CAE(计算机辅助工程)
| DV 【中】设计验证(DV) | Comp 【中】零件级(Comp) | PHM
| PV 【中】工艺验证(PV) | Sub-System 【中】子系统 | PT 【中】样件(工装件)
|  | System 【中】系统 | Pre-VP 【中】量产前验证(Pre-VP)
|  | Vehicle 【中】车型 | FDV 【中】功能开发车(骡车)
VP 【中】量产验证(VP)
PVP
Job 1 Offline 【中】量产首件下线(Job1)
V1
Alpha 【中】Alpha样
Beta 【中】Beta样
Gamma 【中】Gamma样
Pre-Pilot 【中】预试产
Pilot 【中】试产(Pilot)